## Ben
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25/18-2/1/18 | 5 | 3.5 | 1.5 | 0 - learning about the stack 5 - organizing group materials 6 - setting up the platform we will be usin | 1 |  |  |  |  | 0.5 | 2 | 0 - learning the stack 5 - work on SPPP 6 ssetup github etc. | 4
2/1/18-2/8/18 | 8.5 | 6.5 | 2 | 0 - continue learning the stack 5 - doing my best to lead 6 - write my parts of the SPPP, proofread entire SPPP [we all did] | 3 |  |  |  |  | 0.5 | 3 | 0 - continue learning about MEAN, specifically Angular 2 - begin writing code for the front-end 3 - implement my code after I... 4 - test and retest the code I've written 6 - finally setup my 'platform' | 12
2/8/18-2/15/18 | 8.5 | 6.5 | 2 | 0 - continue learning the stack, MEAN tutorial, Google login API research, Angular tutorial, 5 - doing my best to lead, 6-Continue trying to get my setup working | 4 |  |  |  |  | 0.5 | 2 | 0 - continue learning the stack, Angular tutorial 5 - doing my best to lead, 6-Continue trying to get my setup working Notes - I was away at a convention for the second half of the week … I didn't have as much time to work on school stuff. I will be back to normal hours the following week | 4
2/15/18-2/22/18 | 3.5 | 2.5 | 1 | 0 - Angular tutorial, 5 - doing my best to lead. Notes - I was away at a convention (that's why I missed class) for the second half of the week … I didn't have as much time to work on school stuff. I will be back to normal hours next week. | 2 |  |  |  |  | 0.5 |  | 0 - Angular tutorial, more Google login API research, 2 - design Google login API, 3 - implement Google login API, 5 - doing my best to lead. | 10
2/22/18-3/1/18 | 9.5 | 7.5 | 2 | 0 - Angular tutorial, more Google login API research, 2 - design Google login API, 3 - implement Google login API, 5 - doing my best to lead. | 4 | 1 | 2 |  |  | 0.5 |  | 0 - Angular tutorial, more Google login API research, 2 - design Google login API, 3 - implement Google login API, 5 - doing my best to lead. | 10
3/1/18-3/8/18 | 10.5 | 9.5 | 1 | 0 - Angular tutorial, more Google login API research, 3 - implement Google login API, 5 - doing my best to lead. | 5 |  | 4 |  |  | 0.5 |  | 0 - Angular tutorial, more Google login API research, 3 - implement Google login API, 5 - doing my best to lead. | 10
3/8/18-3/15/18 | 9.5 | 7.5 | 2 | 0 - Angular tutorial, more Google login API research, 3 - implement Google login API, 5 - doing my best to lead. | 4 |  | 3 |  |  | 0.5 |  | 0 - Angular tutorial, more Google login API research, 3 - implement Google login API, 5 - doing my best to lead. | 8
3/15/18-3/22/18 | 8.5 | 6.5 | 2 | 0 - Angular tutorial, more Google login API research, 3 - implement Google login API, 5 - doing my best to lead. | 4 |  | 2 |  |  | 0.5 |  | 0 - Angular tutorial, more Google login API research, 3 - implement Google login API, 5 - doing my best to lead. | 8
3/22/18-3/29/18 | 12.5 | 10.5 | 2 | 0 - Angular tutorial, more Google login API research, non-Google login research 3 - implement Google login API, non-Google login implementation 5 - convert meeting minutes action steps to pivotal trackerdoing my best to lead 6 - collect pivotal tracker data and make my slide for the presentation | 2 |  |  | 3 |  | 0.5 | 5 | 0 - Angular tutorial, more Google login API research, non-Google login research 3 - implement Google login API, non-Google login implementatio, doing my best to lead | 10
3/29/18-4/5/18 | 8 | 5.5 | 2.5 | 0 - Angular tutorial, more Google login API research, non-Google login research 3 - implement Google login API, non-Google login implementatio, doing my best to lead | 3 |  |  | 2 |  | 0.5 |  | 0 - Angular tutorials 3, implement a ''guest'' button on login page, implement the ''guest view'', 5 - do my best to lead, add most stories to pivotal tracker | 8
4/5/18-4/12/18 | 9.5 | 7.5 | 2 | 0-Angular tutorial, learn to implent a guest button and its functionality, 3, try to implement a guest button, 5-discuss in Slack, do my best to lead | 3 |  |  | 3 |  | 1.5 |  | 0-Angular tutorial, learn to implent a guest button and its functionality, 3, try to implement a guest button, 5-discuss in Slack, 6-do my best to lead | 10
4/12/18-4/19/18 | 8.5 | 6.5 | 2 | 0-learn how to write tests in Angular, 4-write tests in Angular, 5-discuss in Slack, do my best to lead | 4 |  |  |  | 1 | 1.5 |  | 2-record my tests in test/bugspreadsheet 4-test ''Continue as Guest'' functionality, 5-talk to group in Slack to make sure everything is completed for 4/26/18, do my best to lead, make sure everyone has all forms completed, 6-write in SDD
4/9/18-4/26/18 | 14 | 12 | 2 | 2-record my tests in test/bugspreadsheet 4-test ''Continue as Guest'' functionality, 5-talk to group in Slack to make sure everything is completed for 4/26/18, do my best to lead, make sure everyone has all forms completed, 6-write in SDD |  |  | 1 |  | 2 | 5 | 4
Totals | 116 | 92 | 24

## Chad
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25 - 2/1/2018 | 12 | 10 | 2 | 0,3,5 | 3 |  |  | 7 |  | 2 |  | FIgure out how to configure our project with Webpack, Material UI, and Mocha/Chai. Finish configuration. Spend more time with the team developint requirements, writing tickets & communicating standards. | 10
2/1/18-2/8/18 | 6 | 4 | 2 | 0 - typescript, handlebars 3 - data modelling 5 - team meetings | 3 |  |  | 1 |  | 2 |  | 1. Get around to Weback, MaterialUI & Mocha/Chai integration. 2. Work to gather requirements & write ticket 3. Continue to work on data models | 8
2/9-2/15/18 | 6 | 4.5 | 1.5 | 0 - deep dive on Mongoose API and MongoDB indexing and query operators 5 - team meeting | 4.5 |  |  |  |  | 1.5 |  | 4. REST endpoint testing
2/16-2/22/18 | 10 | 7 | 3 | 0 - mocha/chai REST unit testing 3 - refactored Mongoose models 4 - implemented REST unit tests 5 - team meetings & helped Ben set up his dev environment | 2 |  | 1 | 4 |  | 3 |  | 0. Advanced Mongoose functionality (aggregations, filters, foreign keys) 3. FInish Projects REST endpoints; begin on Users endpoints 4. Write "non-happy" unit & integration tests for Projects & Users | 8
2/23-3/1/2018 | 6 | 4 | 2 | 0 - mongoose training 3 - refactored controllers 5 - meetings | 2 |  |  | 2 |  | 2 |  | 3. Work on Users & Comments endpoints and controllers 4. "Non-happy" unit & integration tests | 8
3/2/-3/15/2018 | 4 | 2 | 2 | 3 - extended & refactored models 5 - meetings |  |  |  | 2 |  | 2 |  | 3. Merge new branch; finalize Users & Comments models 4. Work on unit & integration tests | 8
3/16-3/22/2018 | 8 | 6 | 2 | 3 - fixed bugs in Project model; updated model; merged fixes to master 5 - meetings & iteration 2 prep |  |  |  | 6 |  | 2 |  | 2. Design Sessions model; 3. Implement Sessions model & controller; fix "delete non-existent project" bug; refactor project structure (code & doc root directories per Midterm Review feedback) 5. Improve documentation (Add SDD per Midterm Review feedback; update SPPP; update ECB Object models); Saturday morning working session with group; Monday night meeting) 6. Work on Iteration 2 presentation | 10
3/23-3/29/2018 | 6 | 4 | 2 | 3 - worked on models 5 - meetings |  |  |  | 4 |  | 2 |  | 4. Fix bugs | 6
3/30-4/5/2018 | 4 | 2 | 3 | 3 - fixed bugs 5 - meetings |  |  |  | 2 |  | 2 |  | Spring break | 0
4/6-4/12/2018 | 0 | [10 empty] | Set up production server | 4
4/13-4/19/2018 | 6 | 4 | 2 | 0 - Mongoose deep dive 5 - meetings 6 - created account & set up prod server | 2 |  |  |  |  | 2 | 2 | Deploy to production server. Project management Documentation | 10
4/20-4/26/2018 | 12 | 8 | 4 | 3 - deployed to dev server; branching & pull request management 5 - meetings, pairing on bugs & updating docs |  |  |  | 8 |  | 4 |  | Begin studying for final | 8
Totals | 80 | 55.5 | 25.5

## Andy
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25 - 2/1 | 10 | 8 | 2 | 0 - MEAN Stack 1 Group Meeting | 8 | 0 | 0 | 0 | 0 | 2 | 0 | Worked through several MEAN STACK tutorials. Ando also mastered components, services, in Angular5 | Not Sure, Based on Learning Pace
2/4 - 2/10 | 7.5 | 6 | 1.5 | 0 - Making several tutorial CRUD Apps, 0 - Tutorial on Angular Material 1 - SPPP Requirements | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | Create the wireframs in Angular MAterial and finalize the front end 'look and feel | 4-5 hours for wireframes
2/11 - 2/17 | 5.5 | 4 | 1.5 | 2 - Create Login Page | 0 | 0 | 4 | 0 | 0 | 1.5 | 0 | Complete the rest of the main pages we will need for the front end | Unknown
2/18 - 2/24 | 5.5 | 4 | 1.5 | 2 - Create Major pages for front end 3 - fix version bugs in angular project | 0 | 0 | 4 | 0 | 0 | 1.5 | 0 | Finish up outstanding issues before presentation on Thursday
2/25 - 3/3 | 12.5 | 11 | 1.5 | 2 - Finished up CRUD features on site, implemented angular material for form 5 - Weekly Hangouts meeting on monday | 0 | 0 | 11 | 0 | 0 | 1.5 | 0 | Work on building out Parker's new Better UI
3/4-3/17 | 3.5 | 2 | 1.5 | 2 - finalize Angular features | 0 | 0 | 2 | 0 | 0 | 1.5 | 0 | Merge branches | 3-4 hours
3/18 - 3/24 | 12.5 | 11 | 1.5 | 0 - Learning User Authentication In Angular 2 - Created User Auth Service in Angular 2 - Built up the Project Search Page 4 - Test User Auth Service in Angular 1 - Create 1 task in pivotal tracker | 3 | 0.5 | 6 | 0 | 1.5 | 1.5 | 0 | Work with Ben to get Google Auth into the app | Unknown
3/25 - 3/31 | 23.5 | 21.5 | 2 | 0 - Review Hashing in javascript (15 min) 0 - State Management in Angular (120 min) 1 - Discuss with Chad how Angular and Express will talk to each other for User Auth (90 min) 2 - Implement User Authentication as an Angular App wide Service (360 mins) 3 - Imbed and Activate Login Page to use Express Authentication API (140 min) 3 - Refactor Code after Express Rest Endpoint Updates (d540641c311089f71a6f7fa3d976fa42258b9550) (45 min) 4 - Test Parker's Branch and Merge into Master (90 min) 5 - Team Meetings Saturday morning for game plan (120 min) 5 - Front End meeting Sunday Night to sync up on action items for andy, ben, parker (120 min) 5 - Team meeting Monday night to get updates on progress and set deliverables (120 min) 6 - Help Ben Install the Project on his local computer (90 min) 6 - Screen share with Parker to fix some angular bugs he encountered with a branch (45 min) 6 - Assist team members so they can properlly push their code to github (60 min) | 2.25 | 1.5 | 6 | 3 | 1.5 | 6 | 3.25 | Project Search Work with Kanishq on Angular Testing Implement Comments in Angular Work with Kanishq/Chad to hook up Comments to back end | 3 Hours per topic
4/1 - 4/7 | 5 | 1.5 | 3.5 | 5 - Team meeting (120 min) 4 - Review Parker's branch for UI Updates (90 min) 5 - Team meeting (90 min) | 0 | 0 | 0 | 0 | 1.5 | 3.5 | 0 | Fix Security Issues with current User Auth review outstanding pull requests | Unknown
4/8 - 4/14 | 12.5 | 11 | 1.5 | 4 - Review Chad's branch for extra model features (90 min) 3 - HTTPS Activation in Express (120 min) 3 - User Auth Improvement (Login now returns session object, Angular manages User Object) (450 min) | 0 | 0 | 0 | 9.5 | 1.5 | 1.5 | 0
4/15 - 4/21 | 12.5 | 11 | 1.5 | 4 - Review defect management tracker (120min) 5 - Weekly google meeting on monday (90 min) 3 - Angular Front end code refactoring (90 min) 5 - Review Some of code parker is having some trouble on (30 min) 5 - Work with ben to help him push his branch to github (30 min) 2 - SDD Angular and User Auth pieces (90 min) 5 - troubeshoot build on parkers machine chrome issue was cause (240 min) 5 - created outline presentation and assign team members to individual slides (60 min) | 0 | 0 | 1.5 | 1.5 | 2 | 7.5 | 0 | Work on SDD Work on Presentation Work with parker to get his code merged work with ben to get his tests merged | 2-3 hrs per item
4/22 - 4/28 | 27.25 | 25.75 | 1.5 | 4 - Angular Defect Testing defects 105-113 excluding 108 (345 min) 5 - Assisted Parker with build problems on his computer (60 min) 2 - Defect 127 Home page (360 min) 5 - Assisted Chad with AccessControls Branch (90 min) 5 - Weekly google hangouts meeting (90) 3 - Worked With Chad to build angular and deploy on digital Ocean Prod Server (240 min) 4 - Worked through some additional bugs in the Prod enviroment (60 min) 3 - Hardened Certificates and created Mock Certificate Issue called Andy-Security (180 min) 5 - Created Security Powerpoint Slides (120 min) 5 - Review Parkers AccessControls Branch (15 min) 5 - Review Chad's remove column branch (15 min) 3 - Some final Debugging in Production (60 min) | 0 | 0 | 6 | 8 | 6.75 | 6.5 | 0 | Finalize anything outstanding for Submitting the project on thursday | 2-3 Hours
TOTALS | 137.75 | 116.75 | 21 |  | 18.25 | 4.5 | 40.5 | 22 | 14.75 | 34.5 | 3.25

## Parker
Week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | Time for type 0 tasks | Time for type 1 tasks | Time for type 2 tasks | Time for type 3 tasks | Time for type 4 tasks | Time for type 5 tasks | Time for type 6 tasks | Estimated tasks for next week | Total estimated time
1/25 - 2/1/2018 | 10 | 8 | 2 | 0 - Learning the MEAN Stack; 1 - Brainstorming the app features 5 - Meeting with the group members | 6 | 2 | 0 | 0 | 0 | 2 | 0 | > Revise JavaScript and database concepts & > Learn basics of MEAN Stack; > Discussing the work flow and the design | 8
2/1/18-2/8/18 | 12.5 | 11 | 1.5 | 0 - Revising JavaScript, Learning Node.js; 2 - Design Analysis 3 - Setting up the MEAN stack 5 - Group meeting | 6 | 2 | 1 | 2 | 0 | 1.5 | 0 | > Learn (coding) Node.js+Angular.js+MongoDB > Design the data flow and architecture > Discuss the data flow with the group members | 12
2/9/18-2/15/18 | 14.5 | 13 | 1.5 | 0 - Learning Node.Js with Handlebars 2 - Prepared powerpoint presentation showing wireframes 5 - Group meeting | 5 |  | 8 |  |  | 1.5 | 0 | > Learn Node.Js with Angular > Learn Angular | 10
2/16/18-2/22/18 | 14.5 | 7 | 2 | 0 - Node Js tutorials and Mongoose ORM basics 5 - Group meeting | 7 |  |  |  |  | 2 | 0 | > Learn Angular Material CSS > Understand data models for the project > Learn all the Git Commands | 10
2/23/18-3/2/18 | 11.5 | 10 | 1.5 | 0 - Started Learning Angular Material CSS 0 - Understanding the base project code | 10 |  |  |  |  | 1.5 | 0 | > Learn Component creation and working with templates in Angular JS > Learn all the GIT commands | 10
3/3/18-3/15/18 | 12.5 | 11 | 1.5 | 0 - Started Angular tutorials (Youtube) 0 - Git Basics 5 - Group Meeting 6 - Prepare presentation | 10 |  |  |  |  | 1.5 | 1 | > Learn Angular NG modules and data binding in Angular JS > Learn Event binding in Angular JS > CSS | 12
3/16/18-3/23/18 | 22 | 19.5 | 2.5 | 0 - Angular NG Modules 0 -Cascaded Style Sheets 3 -Created 'Create Account Component' 3 -Created create user service. 4 -Test Kanishka's API and UI Test branch 5 -Group Meeting 5 -Meeting with Andy to clear doubts about the project dataflow. | 12 |  |  | 6 | 1.5 | 2.5 |  | > Learn Google Login API Integration > Create 'Show Projects' component | 10
3/24/18-3/29/18 | 30 | 27.5 | 2.5 | 0 - Studied GoogleLogin API Integration 3 - Created the 'Show Projects Page' 3 - Updated the 'Login Page' UI and added additional functionalities 3 - Added 'Guest User' login 3 - Updated the User Profile page. 3 - Fixed page redirection issues. 4 - Test and review Andy's branch. 5 - Group meeting 5 - Meeting with Ben and Andy to discuss angular Status (March 25) 5 - Meeting with Andy to discuss the new 'Show Projects' component (March 28) 6 - Prepare Presentation - Key Highlights of the Sprint and Code Coverage | 3 |  |  | 24 | 0.5 | 2.5 |  | > Learn Server and Client State Management > Work on 'Show Projects' page and access controls | 12
3/30/18-4/05/18 | 8 | 6.5 | 1.5 | 2 - Re-designed and implemented the 'Show Project' component. 3 - Wrote servicies to get project by name and by Id. 3 - Fixed the getProjectByName controller to return the projecrtId also which was previously returnin gonly names. 3 - Deleoped the 'Show Projects' component to retun the list of projects. 4 - Tested the Show Projects locally. 5 - Group Meeting on Hangouts |  |  | 3 | 2 | 1.5 | 1.5 |  | > Work on the search project functionality of the 'Show Project' component
4/06/18-04/12/18 | 6.5 | 5 | 1.5 | 3 - Refactored the typescipt code for 'Show Project'. 3 - Worked on the design & implementation of projects access controls. 4 - Tested Andy's Security Branch 5 - Discussed the modification of models (projects and user) with Chad, that will make it possible to assiciate the projects with the users (owners and members) 5 - Weekly monday meeting. |  |  |  | 4 | 1 | 1.5 |  | >Continue working on Show Project Component
04/13/18-04/19/18 | 9 | 7.5 | 1.5 | 3 - Completed the 'Show project' component- Project search list and projects populating correctly. 4 - Tested and reviewd Andy's Security updates. 5 - Wekly meeting 5 - Worked with Andy to fix the security expection problem in my system. |  |  |  | 7 | 0.5 | 1.5 |  | >Fix the incomplete-data retrieval problem >Work on the defects in the defects/bug sheet >Separate the search project and show project functionality code for reusability >Create Slides for final presentation >Learn details about Angular Obsevable and Promises.
04/20/18-04/26/18 | 23 | 22 | 1 | 0 - Learned in detilas about the Observables to deal with the latency in data retieval on the webpage. 3 - Created a new subcomponent - 'Project Box' for 'Show Project' component. Project Box is now a reusable component to show the project details anywhere on the website. 3 - Fixed on the asynchronous data latency problem faced by Chad, Andy and Kanishka. 3 - Created the logs 4 - Worked on defects assigned by Kanishka- 122-126 and 128-132. 5 - Weekly meeting on Hangouts. 6 - Created the 'Requirement Analysis'and 'Workflow' slides. | 2 |  |  | 10 | 8 | 1 | 2 | RELAX

## Kanishka
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
Week 2 (1/25 - 02/01) | 6 | 5 | 1 | 0 - Learning the new technologies of the MEAN Stack 3 - Implementing the Story Management in PivotalTracker | 3 |  |  | 3 |  |  |  | 0 - Learning the implementation of the MEAN stack 2 - Designing the UI layout 5 - Team Meeting, | 8
Week 3 (02/02 - 02/08) | 10.5 | 9 | 1.5 | 0 - Ramping up on Node and Angular 2 - Design of the High Level workflow documentation 1 - Preparing the SPPP document | 4 | 3 | 2 |  |  |  |  | 0 - Learning the implementation of the MEAN stack 6 - Test Planning Document 3 - Implementation of APIs | 10
Week 4 2/9-2/15/18 | 9 | 7 | 2 | 0 - Ramping up on the new back end Architecture 1 - User Story Development 2 - Designing workflows for use case | 3 | 2 | 1 |  |  |  |  | 0 - Understanding the new architecture, the design flow 3 - Development | 6
Week 5 2/16-2/22/17 | 7 | 5 | 2 | 0 - Ramping up on the new front end Architecture 1 - User Story 3 - Test framework ramp up and development | 2 | 1 | 2 |  |  |  |  | 0 - Understanding the new architecture, the design flow 3 - Development | 8
Week 6 2/25-3/3 | 7 | 5 | 2 | 0 - Learning the new automation tools 4 - Testing the API | 3 |  | 2 |  |  |  |  | 0 - Understanding the new architecture, the design flow 3 - Development
Week 7 3/4-3/17 | 6 | 5 | 1 | 0 - Learning the new code collaborator tool Research and implementation on the UI automation tool 4 - Automating the API tests | 4 |  |  | 1 |  |  |  | 3 - Automation development | 5
Week 8 3/18-3/25 | 16 | 14 | 2 | 0 - Learning new automation tools 1. User Story creation 3 - Test Automation implementation 3 - API route update. Controllers and models for Project 4 - API and UI Testing | 2 | 1 |  | 6 | 5 |  |  | 3 - Automation development | 5
Week 8 3/26-4/02 | 11 | 13 | 2 | 0 - Learning new automation tools 1. User Story creation 3 - Test Automation implementation 3 - API route update. Controllers and models for Project 4 - API and UI Testing | 1 | 1 |  | 6 | 3
Week 9 4/03 - 4/09 | 4 | 2.5 | 1.5 | 4 - API and UI Testing |  |  |  |  | 2.5
Week 10 4/11 - 4/16 | 10 | 8 | 2 | 4 - Testing. Defects logging and verification 5 - Co-ordination and prioritization of Tasks, |  |  |  |  | 7 | 1
Week 11 4/17 - 4/26 | 15 | 12 | 3 | 4 - Testing. Defects logging and verification 5 - Co-ordination and prioritization of Tasks, 6 - Demo Preparation |  |  |  |  | 9 | 2 | 1

## Midterm Contribution Report
StudentName | Requirement Analysis on Pivotaltracker | SPPP Document | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (testing code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Chad Cover | Helped write REST API stories for project creation & view. |  | Wrote README file to faciitate dev environment setup. Committed Data Models Entity Class diagram. |  | Gave part of Iteration 0 presentation. Gave "Git Basics" presentation. | Initial commit of front- and back-end branches. Refactored models & controllers. | Wrote integration tests for Project REST calls. | Set up GitHub project. Deployed master branch.
Andy O'Connell | -wrote user story about a user searching for a specific project -Wrote user story for admin to change ownership of project | High Level Design Section |  |  | Gave live demo during iteration 1 presentation | Build the angular components, services, and integrated Angular Material into the project | High level spec testing of angular components | worked through package issues that caused issue when installing from older versions of npm | Meeting Note taker 2/19
Kanishka Bagri | Set up on the pivotal tracker for the team, Wrote the user story for REST API projects | Quality Assurance Plan Metrics Standard Inspection/Review Process Testing Defect Management Process improvement process |  |  | Gave the live Demo on the overall architecture of the Project Portal | Added the following: 1. Integration tests for the Project API 2. Added the Istanbul/nyc as Code collaborator tool for the project 3. Added the UI automation tool and the initial tests to validate UI components | 1. Manual Testing of APIs 2. Maual testing of UI components and features 3. Automated tests of APIs 4. Automated validation of UI 5. Automate code coverage install and calculation | 1. Setup UI automation tool 2. Setup of code coverage tool | Meeting Notes and communication with the customer to clarify requirements
Parker |  | Management Plan Section |  |  | Prepared Wireframes for the project

## Final Contribution Report
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Kanishka Bagri |  | Quality Assurance Plan Metrics Standard Inspection/Review Process Testing Defect Management Process improvement process |  | All the sections: Introduction Test Summary Tests Reports Testing Metrics References Glossary | 1. Gave the live Demo on the overall architecture of the Project Portal, 2. Presented the Quality Aspects of the Projects in each Demo 3. Recorded the final Demo also, 4. Presented the final Demo with another team member | Added the following: 1. Integration tests for the Project API 2. Added the Istanbul/nyc as Code collaborator tool for the project 3. Added the UI automation tool and the initial tests to validate UI components | 1. Manual Testing of APIs 2. Maual testing of UI components and features 3. Automated tests of APIs 4. Automated validation of UI 5. Automate code coverage install and calculation | 1. Setup UI automation tool 2. Setup of code coverage tool | Meeting Notes and communication with the customer to clarify requirements | Driving the overall Testing Strategy, implementation of Testing and Defect Management cycle, Taking up the role of a Scrum Master from to co-ordinate the flow of tasks for improving overall quality of the product in the agreed time line
Andy O'Connell |  | Created Tickets as I worked through Impelemntation and Defects | Angular Front End and User Authentication |  | 1. Created the origional presentation outline 2. Presented Security and Encryption for the Ap | 1. Express HTTPS 2. Public Private Key Creation 3. User Auth 2.0 4. Front End Code Refactoring 6. Hardened Certificates and created Mock Certificate Issuer called Andy-Security | 1. Reviewed 6 Pull requests that Team members submitted 2. Fixed 10 Defects from Kanishka's defect tracker | 1. Worked with chad to deploy App to digitalOcean Production Server 2. Created origional Prod Branch to allow angular to route properlly | 1. Weekly Meeting Note Taker March 25 | 1. Became the SME for Angular. 2. Devoted 8.5 Hours helping and advising teammembers on things related to Github and Angular
Prabhakar Punj Lal |  | Worked on the tasks assigned to me by other team members. | Use Case Diagram |  | 1) Create the 'Requirement Analysis' ,Project overview Slides, 'Non-Functional Requirements', 'User Stories Statistics' and 'Workflow' slides. | 1. Create Account Component 2.Show Project Component 3.Project Box Component 4.Services related to the above components 5.Login Page (UI Only) | 1. Tested and fixed the defects assigned to me by kanishka. Defects: 122-126 and 128-132 2. Fixed the data retrival latencty due to asnchronous behavoir of Node.js code.
Ben |  | Added many [17] user stories and assigned the to the member[s] responsible | membhers' names, some formating, introduction |  | WQas incompassitated at tyhe end of the day, so I just prepared my remarks and presented my the 3 slides for which I was responsible | some of the angular component testing | wrote a few automata for angular components and manually tested 'Login' and 'Continue as Guest' buttons |  | Was the best team Leader I could be; facilitated mmeeting, lauded teammates where appropriate, reminded members to complete their paperwork [weekly, post-iteration,...], rotated minutes-keeper, voluteered to help anyone I could [they were too good and didn't need me] | **Please see post-interation review**
Chad Cover |  | Closed a number of tickets | Wrote Software Architecture section, Designed ECB diagram and User & Session Class Model Diagrams, edited entire document, suggested content for resources and glossary |  | Design, Implementation, and Production Environment slides | A few tests, Refactored backend models and controllers, primary code reviewer and GitHub manager, refactored one Angular component to remove a redundant link and extraneous component. |  | Purchased and built production server on Digital Ocean; worked with Andy to deploy production code; implemented strong user auth on MongoDB on production server. | Very active on Slack during the end of iteration, helping others to check in their branches & resolve merge conflicts; took minutes when it was my turn. | Feel like I did my performed my role as Configuration & Environment Integration lead quite well. Set up GitHub as well as the entire stack in Iteration One. Coded most of the backend. And set up the production server. Was quite glad to work with this group. Were I to do this again, I'd have pushed harder to use React on the frontend, as I know it, and with my focus on the backend, didn't get the change to learn as much Angular as I'd hoped.